## Gantt Chart
Senior Design Gantt Chart | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | MoDNS |  |  |  |  | COMPANY NAME | [6 empty] | LaTech Senior Design
PROJECT MANAGER |  | Seth Warren |  |  |  |  | DATE | [6 empty] | 2022-12-20
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FIVE | [14 empty] | PHASE SIX
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 17 |  |  |  |  | WEEK 18
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Research and Preliminary | [5 empty] | 2023-12-19 | 2023-12-20 | 2023-12-21 | 2023-12-22 | 2023-12-23 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-03 | 2023-04-04 | 2023-04-05 | 2023-04-06 | 2023-04-07 | 2023-04-10 | 2023-04-11 | 2023-04-12 | 2023-04-13 | 2023-04-14 | 2023-04-17 | 2023-04-18 | 2023-04-19 | 2023-04-20 | 2023-04-21
1.1 | Research DNS | Seth Warren | 2022-12-26 | 2023-01-06 | 14 | 0% | bar: WEEK 2 M to WEEK 3 F
1.1.1 | Research Rust Programming Language | Bronson Jordan | 2022-12-19 | 2023-01-06 | 7 | 0% | bar: WEEK 1 M to WEEK 3 F
1.2 | Research Plugin Implementation Plans | Bronson Jordan, Seth Warren | 2022-12-26 | 2023-01-06 | 14 | 0% | bar: WEEK 2 M to WEEK 3 F
1.3 | Create Frontend Concept Map | Carter Ray, Aankit Pokhrel | 2022-12-19 | 2023-01-06 | 21 | 60% | bar: WEEK 1 M to WEEK 3 F
1.4 | Create Backend Concept Map | Seth Warren | 2022-12-19 | 2023-01-06 | 21 | 0% | bar: WEEK 1 M to WEEK 3 F
1.5 | Create Repository | Seth Warren | 2022-12-19 | 2022-12-19 | 1 | 100% | bar: WEEK 1 M
1.6 | Create API Concept Map | Timothy Huhn | 2022-12-19 | 2023-01-06 | 21 | 0% | bar: WEEK 1 M to WEEK 3 F
2 | Development
2.1 | Frontend Development | Carter Ray, Aankit Pokhrel | 2023-01-09 | 2023-03-03 | 28 | 0% | bar: WEEK 4 M to WEEK 11 F
2.2 | DNS Backend Development | Bronson Jordan | 2023-01-09 | 2023-03-03 | 28 | 0% | bar: WEEK 4 M to WEEK 11 F
2.3 | API Development | Timothy Huhn | 2023-01-16 | 2023-03-10 | 28 | 0% | bar: WEEK 5 M to WEEK 12 F
2.4 | Plugin Implmentation | Seth Warren | 2023-01-16 | 2023-03-10 | 28 | 0% | bar: WEEK 5 M to WEEK 12 F
2.5 | Default Plugins | All | 2023-01-16 | 2023-03-10 | 28 | 0% | bar: WEEK 5 M to WEEK 12 F
3 | Prototype and Testing
3.1 | Creating & Configuring Docker Containers | Bronson Jordan | 2023-03-13 | 2023-03-24 | 14 | 0% | bar: WEEK 13 M to WEEK 14 F
3.2 | Testing Implementations | Timothy Huhn | 2023-03-13 | 2023-03-24 | 14 | 0% | bar: WEEK 13 M to WEEK 14 F
3.2.1 | Frontend Testing | Aankit Pokhrel | 2023-03-13 | 2023-03-24 | 14 | 0% | bar: WEEK 13 M to WEEK 14 F
3.2.2 | Backend Stresstesting | Seth Warren | 2023-03-13 | 2023-03-24 | 14 | 0% | bar: WEEK 13 M to WEEK 14 F
3.3 | Project Updates | Seth Warren | 2023-03-27 | 2023-03-31 | 0 | 0% | bar: WEEK 14 M to WEEK 15 F
3.3.1 | Chart Updates | Carter Ray | 2023-03-27 | 2023-03-31 | 0 | 0% | bar: WEEK 14 M to WEEK 15 F
4 | Optimization and Maintenance
4.1 | Optimization | Bronson Jordan | 2023-04-03 | 2023-04-21 | 0 | 0% | bar: WEEK 16 M to WEEK 18 F
4.2 | Bug Fixing | Carter Ray, Seth Warren | 2023-04-03 | 2023-04-21 | 0 | 0% | bar: WEEK 16 M to WEEK 18 F
4.3 | Documentaion | Timothy Huhn | 2023-01-09 | 2023-04-21 | 0 | 0% | bar: WEEK 4 M to WEEK 18 F
4.4 | Updating Concept Maps | Aankit Pokhrel | 2023-04-03 | 2023-04-21 | 0 | 0% | bar: WEEK 16 M to WEEK 18 F